## Product backlog
Project name: X-Fighter
Development tool:
User stories | Priority (1-3)
As a game player, I want to control my plane, so that the plane can go everywhere . | 3 | Lan
As a game player, I want my plane to shoot all the time automatically, so that I can kill enemy plane. | 3
As a game player, I want enemy planes to come from opposit direction towards my plane so that I have a goal to shoot. | 3 | Claudia
As a game player, I want enemy planes disapper when my bullet hit them so that the goal is achieved. | 3 | Ling
As a game player, I want a score sheet so that I can track the progress. | 3 | Swati
As a game player, I want the game over when my plane is hit by enemy plane so that the game is over. | 3 | Ruiyun
put new user stories here discuss tomorrow:
As a game player, I want some music when I play this game so that it makes this game more intresting and vivid.
As a game player, I want there is an explosion animation whenever there is a collsion so that the game is more intresting and vivid.
As a game player, I want to pause and resume the game so that I can go away for a while.
Note on B4: Author: 1 means high priority 3 menas low priority

## Sprint backlog
Sprint 1 backlog |  |  |  | Hours of Work Remaining on Each Day of the Sprint
Backlog Item | Task | Task Owner | Initial Estimate | Day 1 | Day 2 | Day 3 | Day 4
Control my plane | Design my plane image |  | 0.5 | 4
| Design control logic and implement the code 1. Plane moves left/right/up/down at a proper speed as player presses the arrow key, otherwise keeps still 2. Keep plane within the screen while it moves |  | 4 | 4
4
4
My plane shoots all the time automatically | Design the bullet image |  | 0.5 | 4
| Design the shooting logic and implement the code 1. Plane keeps shooting at a proper speed |  | 0.5 | 4
| Design bullet logic and implement the code 1. Bullet moves forward at a proper speed and disappears in one second after it is emitted 2. Bullet disappears once it hits any object in the screen, or touches the boundary of the screen within its lifetime |  | 4 | 4
4
As a game player, I want enemy planes disapper when my bullet hit them so that the goal is achieved. | bulletListener track the movement of bullets |  | 2 | 4
| set bullet emittion speed |  | 1 | 4
| Enemy planes disappear from the space wheh bullet hit them |  | 3 | 4
| Enemy planes explore when be hitted ( just an additional feature) |  | 2 | 4
|  |  | 4 | 4
|  |  | 4 | 4
|  |  | 4 | 4
|  |  | 4 | 4
|  |  | 4 | 4
|  | Total | 37.5 | 68 | 0 | 0 | 0

## Day 1
[team name], sprint 1
Team member name
Lan Xu
What I did since last daily scurm:
-
-
What I plan to do today:
-
-
What blockers I have:
-